## Dark
Mid Bootcamp Project: Classification Problem
Ironhack |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-12-14 |  |  |  |  | December | [20 empty] | January | [27 empty] | February
Scrolling Increment: | 0 | time axis 2021-12-14 to 2022-02-07
Milestone description | Category | Assigned to | Progress | Start | Days | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Mid Bootcamp Project TimeFrame | On Track |  | 4% | 2021-12-11 | 29
Project Kick-off |  |  |  | 2021-12-11 | 1
Gantt Chart of the Project | Milestone | Albert | 75% | 2021-12-11 | 1
GitHub Repo | Milestone | Albert | 100% | 2021-12-11 | 1
Data Exploration |  |  |  | 2021-12-11 | 6
SQL queries | Low Risk | Albert | 100% | 2021-12-11 | 4
MySQL file delivery | Milestone | Albert & Guillermo | 100% | 2021-12-11 | 1
Exploration with Python | Low Risk | Albert & Guillermo | 0% | 2021-12-14 | 3
Data cleaning | Low Risk | Albert & Guillermo | 0% | 2021-12-14 | 3
Data Pre-Processing | Med Risk | Albert & Guillermo | 0% | 2021-12-14 | 3
Clean & Ready dataset | Milestone | Albert & Guillermo | 0% | 2021-12-16 | 1 | bar: T
ML model |  |  |  | 2021-12-16 | 6
Feature engineering | Med Risk |  | 0% | 2021-12-16 | 3
Logistic regression | Med Risk |  | 0% | 2021-12-18 | 1
Evaluation of the model | High Risk |  | 0% | 2021-12-18 | 4
ML model report | Milestone |  | 0% | 2021-12-18 | 1 | bar: S
Visualization with Tableau |  |  |  | 2021-12-12 | 10
Tableau questions | Low Risk |  | 0% | 2021-12-11 | 4
Dashboard with Model Outcome | Med Risk |  | 0% | 2021-12-15 | 7
Dashboard delivery | Milestone |  | 0% | 2021-12-21 | 1 | bar: T
Final Presentation | High Risk |  | 0% | 2022-01-08 | 1
To add more data, Insert new rows ABOVE this one

## About
ABOUT THIS GANTT CHART
Visualise and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the Milestone Description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use Progress to add how much of the project you finished by adding a percentage number. • Add the day you started your project in the Start Date. • Finish your calculations by filling in the number of days you need to complete your project in the No. of Days field.